## Sheet1
Schedule Management
Team-03, Section-02, Dr. Denise Case
Project Name: Lost Treasure | Date: 08/23/2020
Client Name: Dr. Charles Hoot
Project Manager: Rajeshwari Rudravaram
Start Date: 08/19/2020
End Date: 12/09/2020
Work Breakdown Structure Categories | Start Date | End Date | Estimated Hours per person | [5 empty] | Total
|  |  | Rajeshwari | Vishal | Nooka Raju | Chandrakanth | Rohith | Puneeth
1. Initiating | 2020-08-19 | 2020-08-20 | 1 | 1 | 1 | 1 | 1 | 1 | 6
2. Planning | 2020-08-20 | 2020-08-22 | 2 | 1 | 1 | 1 | 2 |  | 7
3. Designing | 2020-08-22 | 2020-10-15
3.1 UI Design | 2020-08-22 | 2020-08-30 |  |  |  | 3 |  | 2 | 5
3.2 Synthesis of Design | 2020-08-30 | 2020-09-12 | 2 | 2 |  |  |  | 1 | 5
3.3 Implementation Iteration | 2020-09-12 | 2020-09-26 | 2 |  | 2 |  | 2 |  | 6
3.4 Early release and Contract finalization | 2020-09-27 | 2020-10-15 | 2 | 1 | 2 |  |  |  | 5
4. Implementation | 2020-10-16 | 2020-11-20
4.1 Application Development | 2020-10-16 | 2020-10-30 | 1 |  |  | 2 | 4 | 1 | 8
4.2 PWA Implementation | 2020-10-30 | 2020-11-12 |  | 3 |  | 1 | 1 |  | 5
4.3 Android/iOS Implementation | 2020-11-13 | 2020-11-20 |  |  | 5 |  |  |  | 5
5. Monitoring and Controlling | 2020-11-21 | 2020-12-01 |  |  |  | 2 |  | 5 | 7
6. Closing | 2020-12-02 | 2020-12-09 | 2 | 2 |  |  | 2 |  | 6
|  | Total | 12 | 10 | 11 | 10 | 12 | 10 | 65